## US-AC Tracking
SC Code | Screen code | Screen name | US+AC File | Assigned Member | CR-01 Status
SC_001 | AD-00 | Login | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_002 | AD-00b | Account activation | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_003 | AD-15 | 2-step verification | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_004 | AD-01 | User list | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_005 | AD-02 | Create/edit user | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_006 | AD-03 | Role & permission matrix | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_007 | AD-05 | Facility settings | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | MUST HAVE — Planned (v1.3: AD-05 gains tab 'Facility Info' + tab 'Holidays'; tab 1 content unchanged, tab 2 = SC_046)
SC_028 | M2-US-02b | LOC gate | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_008 | AD-06 | LOC rate table | us-ac-sc008-016.docx | Phan Thanh Loc | No Impact (CR-01)
SC_009 | AD-07 | Staffing ratio | us-ac-sc008-016.docx | Phan Thanh Loc | CUT (2026-07-13) — reference-only badge, no logic change; US+AC replaced with cut-note in sc008-016.docx
SC_010 | AD-08 | Incident severity levels | us-ac-sc008-016.docx | Phan Thanh Loc | No Impact (CR-01)
SC_011 | AD-09 | SLA configuration | us-ac-sc008-016.docx | Phan Thanh Loc | No Change — see OI-01 (note added, file sc008-016)
SC_012 | AD-10 | Demo data seeder | us-ac-sc008-016.docx | Phan Thanh Loc | No Impact (CR-01)
SC_013 | AD-16 | Equipment & supply inventory | us-ac-sc008-016.docx | Phan Thanh Loc | SHOULD HAVE — Planned (US+AC drafted, file sc008-016)
SC_014 | SH-US-01 | Dashboard - Nurse | us-ac-sc008-016.docx | Phan Thanh Loc | No Impact (CR-01)
SC_015 | SH-US-01 | Dashboard - DON | us-ac-sc008-016.docx | Phan Thanh Loc | COULD HAVE — Backlog, chờ OI-03 (note added, file sc008-016)
SC_016 | SH-US-01 | Dashboard - CNA | us-ac-sc008-016.docx | Phan Thanh Loc | No Impact (CR-01)
SC_017 | M1-US-01 | Resident list | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_018 | M1-US-02 | Resident profile detail | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_019 | M1-US-03 | Create/edit resident | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_020 | M1-US-04 | Pre-admission screening | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_021 | M1-US-05 | Admission form | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_022 | M1-US-06 | Initial assessment | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_023 | M1-US-07 | Assessment history | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_024 | M1-US-08 | LOC classification | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_025 | M1-US-09 | LOC history | us-ac-sc017-025.docx | Huynh Ngoc Thien | No Impact (CR-01)
SC_026 | M2-US-01 | Care plan list | us-ac-sc026-034.docx | To Duy Bac | No Impact (CR-01)
SC_027 | M2-US-02 | Care plan create | us-ac-sc026-034.docx | To Duy Bac | No Impact (CR-01)
SC_029 | M2-US-03 | Care plan detail | us-ac-sc026-034.docx | To Duy Bac | No Impact (CR-01)
SC_030 | M2-US-04 | DON review | us-ac-sc026-034.docx | To Duy Bac | No Impact (CR-01)
SC_031 | M2-US-04b | E-signature popup | us-ac-sc026-034.docx | To Duy Bac | No Impact (CR-01)
SC_032 | M2-US-05 | Daily task list | us-ac-sc026-034.docx | To Duy Bac | CUT (2026-07-13) — reference-only icon, no logic change; US+AC replaced with cut-note in sc026-034.docx §6.1
SC_033 | M2-US-06 | Bedside vitals | us-ac-sc026-034.docx | To Duy Bac | SHOULD HAVE — Planned (US+AC drafted §6.2, file sc026-034)
SC_034 | M2-US-07 | Reassessment | us-ac-sc026-034.docx | To Duy Bac | SHOULD HAVE — Planned (US+AC drafted §6.3, file sc026-034)
SC_035 | M2-US-09 | Cost/billing panel | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | No Impact (CR-01)
SC_036 | M2-US-10 | IDT acknowledgment | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | No Impact (CR-01)
SC_037 | M7-US-01 | Report incident | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | No Impact (CR-01)
SC_038 | M7-US-02 | Chart lock confirmation | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | No Impact (CR-01)
SC_039 | M7-US-03 | Incident detail | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | CUT (2026-07-13) — reference-only badge, no logic change; US+AC replaced with cut-note in sc035-044.docx
SC_040 | M7-US-04 | Incident list | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | CUT (2026-07-13) — reference-only indicator, no logic change; US+AC replaced with cut-note in sc035-044.docx
SC_041 | M7-US-06 | Submit external report | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | No Impact (CR-01)
SC_042 | M7-US-07 | Chart unlock | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | No Impact (CR-01)
SC_043 | M7-US-03b | Incident detail unlocked | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | CUT (2026-07-13) — reference-only badge, no logic change; US+AC replaced with cut-note in sc035-044.docx
SC_044 | M7-US-03 | Incident detail nurse | us-ac-sc035-044.docx | Nguyen Thi Phuong Thao | CUT (2026-07-13) — reference-only badge, no logic change; US+AC replaced with cut-note in sc035-044.docx
SC_045 | M2-US-02c | Add Custom Care Area Popup | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | No Impact (CR-01)
SC_046 | AD-05 | Facility settings — tab Holidays | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | MUST HAVE — Planned (v1.3, 2026-07-13: real tab 2 of AD-05, reverted from standalone AD-17; 2026-07-14: Status column changed pill+link -> real on/off toggle; US+AC updated §6.1, file sc001-007_sc028 to match toggle UI)
SC_047 | AD-05 | Add/Edit State Holiday Popup | us-ac-sc001-007_sc028_sc045-047.docx | Kieu Quang Van | MUST HAVE — Planned (new 2026-07-14, popup shared for Add + Edit State Holiday, opens from SC_046; US+AC drafted §6.2, file sc001-007_sc028)